Western Extension Directors Association
Video/Multimedia Production

December 2, 2022

## Project Summary

To support WEDA’s goal of developing new informational video/multimedia and updating its existing Extension Employee Onboarding Modules, OSU’s Professional and Continuing Education team proposes the following:

Phase 1 – Introductory/Overview Videos

By spring 2023, PACE would provide two engaging, state-of-the-art videos:

- The Land Grant University System

- The Cooperative Extension System

In terms of design and concept, the two videos may be viewed as part of an overarching, connected narrative highlighting the role of Extension. To address a gap often found in existing historical documents and multimedia, our land grant narrative will include the history of land acquisition and Native American perspectives. Our Extension narrative will take a lively approach to sharing highlights, explaining funding and more.

While overview videos will be developed with Extension stakeholders in mind, our compelling narrative and world-class production values will help engage a far wider audience. To support this effort, our team will place videos on YouTube, on the WEDA website. We will also develop a marketing plan to increase visibility and awareness.

The takeaway? A fresh, energetic and thoroughly modern look at the legacy of the land grant system and Extension that orients stakeholders toward our relevance and impact today.

Phase 2 – Extension Employee Onboarding Modules Redesign

By fall-winter 2023, PACE would provide new/updated Extension Employee Onboarding Modules for the WEDA website. We understand that this effort will involve reconfiguring and supplementing existing modules. Among other things, the end result will reflect the geographic and demographic diversity of Extension and add substantial coverage of DEI/cultural competency.

Proposed Deliverables and Costs>>

## Proposed Deliverable and Costs

While estimated costs are preliminary overall, we anticipate production for phase 1 (introductory/overview videos) should be relatively straightforward. In both cases, PACE will provide overall project management, as well as video production.

Phase 1 – Introductory/Overview Videos

| Deliverables | Total |
| --- | --- |
| Production of two videos (each no more than five minutes in duration). Placement on YouTube, WEDA and any affiliated sites, as needed. Optimization for search engine visibility. | $5,750 - $7,200 |

Assumptions:

- Scripting/concept would be mostly, if not entirely, provided in draft form to PACE production team. The PACE team will advise/provide guidance as part of a collaborative process designed to ensure the finished product achieves desired messaging objectives.

- Videos could incorporate elements such as voiceover narration, multiple (2-3) featured (on-camera) speakers*, dynamic type treatments/elements. We could anticipate use of complementary scenic imagery that may be curated from Extension or from stock video providers. 

* Higher number of on-camera speakers (beyond 2-3 per video) would be significant variable in terms of time/editing and cost.

For featured on-camera speakers, PACE would coordinate filming/recording to ensure quality control.

Phase 2 – Extension Employee Onboarding Modules Redesign

This effort will include redevelopment – and expansion – of the existing onboarding modules. Project objectives include high-quality production and consistent WEDA branding throughout. Because of the educational nature of the modules, we may engage PACE’s instructional design team to advise consistent elements to optimize the learner experience.

Because of the number of individual videos anticipated (~25), we may recommend an approach to help scale up production. For example, standardizing some design elements may be helpful. We may engage content leads (and speakers) to help co-create content for each module. For example, we could feature one “lead” speaker or narrator for each video – and that person may contribute presentation materials/graphics for the video. As with phase 1, our assumptions would include “scripting” for each module to be largely provided by subject matter leaders or featured speakers.

Though it would be difficult to provide an estimate for phase 2 production without more information, we do want to affirm our strong interest in the project. Our intent would be to work within WEDA’s budget – using efforts like those described above to streamline production as needed while ensuring objectives for the modules are fully addressed.

## Example Videos

Examples provided below reflect a range of development inputs. These include fully (pre)scripted narration in some instances and interview-based narration in others. These examples also include varying use of imagery and dynamic edits, background music and so forth.

- Program/service overview (Recovery Iowa)

- Educational video (OSU technical writing portfolio)

- Certificate program overview (Turfgrass Management)

.